# GateShield — Complete Product Inventory, Multi-Company SaaS Architecture, AWS Deployment & Migration Roadmap

Document Purpose: This document contains the complete, unabridged GateShield roadmap and product audit in a clean, structured format for offline reading and implementation planning. Nothing has been skipped, shortened, or removed.

Strict Planning Notice: This document is a planning and architectural roadmap. No application code, database records, or environment settings have been modified to produce this document.

# Table of Contents

• Part I: Executive Guide, Plain-English Glossary & Work Status Breakdown

◦ Section A: Plain-English Glossary of Technical Terms

◦ Section B: Complete Separation of Completed Work, Partially Completed Work, Planned Multi-Company Features & AWS Deployment Tasks

• Part II: Complete Multi-Company SaaS Architecture, AWS Deployment & Migration Roadmap (Sections 1 to 17)

◦ 1. Executive Summary

◦ 2. Current Architecture (Verified Codebase Baseline)

◦ 3. Desired Multi-Company Architecture (One Shared Codebase + Separate Database per Company + Central Super Admin DB)

◦ 4. Recommended AWS Architecture (Including FastAPI + PaddleOCR Hosting Deep-Dive)

◦ 5. Current vs. Desired Architecture Comparison

◦ 6. Complete List of Required Code Changes (CHG-01 through CHG-10)

◦ 7. Central Super Admin Database and Dashboard Plan (/super-admin)

◦ 8. Company Database Strategy (Shared RDS Instance with Separate Databases vs. Separate RDS Instances)

◦ 9. OCR and Private File Storage Strategy (Amazon S3)

◦ 10. Security and Cross-Company Isolation Assessment

◦ 11. Data Migration Plan (Preserving Existing GateShield Installation as Company #1)

◦ 12. AWS Deployment and Safe Release Strategy

◦ 13. Phased Implementation Roadmap (Phases 0 through 12 — Complete Step-by-Step Guide)

◦ 14. Cost Drivers and Indicative Monthly AWS Cost Scenarios (Scenarios A, B, C & Ultra-Lean Option)

◦ 15. Mandatory Testing and Commercial Launch Checklist

◦ 16. Risks, Dependencies, and Key Owner Decisions Before Implementation

◦ 17. Recommended First Step

• Part III: Complete Baseline Inventory of Existing GateShield Features (Sections 1 to 12 — Completed Work)

◦ 1. Admin Dashboard

◦ 2. Operator Dashboard

◦ 3. Employee Portal

◦ 4. Visitor Management

◦ 5. Special Guest Management

◦ 6. CNIC and Driving Licence Scanning (OCR)

◦ 7. Visitor Cards and QR Codes

◦ 8. Check-In and Check-Out Workflows

◦ 9. Gate and Access Management

◦ 10. Reports and Security Audit Records

◦ 11. Notifications and Approvals

◦ 12. Settings, Watchlist/Blacklist, Localization & Branding

# Part I: Executive Guide, Plain-English Glossary & Work Status Breakdown

## Section A: Plain-English Glossary of Technical Terms

To make this roadmap easy to read for both business owners and developers, here is a simple explanation of every technical term used in this document:

| Technical Term | Simple, Plain-English Meaning |
| --- | --- |
| Multi-Tenant / Multi-Company SaaS | Running one single GateShield software system that serves many different client companies at the same time over the internet, where each company sees only its own data, gates, visitors, and staff. |
| Control Plane / Central Super Admin Database (`gateshield_central`) | The master database controlled only by you (the Product Owner). It keeps the list of client companies, whether each company is Active or Suspended, and how the app connects to each company's private database. |
| Tenant Database (`gateshield_tenant_<slug>`) | An individual company's private PostgreSQL database (for example, Company A's database). It holds all of that company's visitors, visits, employees, gates, and badges. |
| Prisma / `PrismaClient` | The database connector tool used by GateShield's Next.js server to read and write records in PostgreSQL databases. |
| LRU Cache (Least Recently Used Cache) | A smart memory manager that keeps active company database connections ready for fast responses and automatically closes idle connections so the database server never runs out of memory. |
| JWT (JSON Web Token) / Session Cookie | A digitally signed security pass stored in the user's browser after login (gk_token or gk_emp_token). In the multi-company version, this pass locks the user to their specific companyId so they can never access another company's data. |
| IDOR (Insecure Direct Object Reference) | A security attack where a user from Company A tries to guess or paste a Visitor ID or Visit ID belonging to Company B in the URL. Separate company databases + locked JWT tokens completely block this. |
| OCR (Optical Character Recognition) / PaddleOCR | The artificial intelligence text-reading engine (written in Python FastAPI) that reads names, CNIC numbers, and dates from photos of Pakistani CNICs and Driving Licences. |
| Base64 Data URL | Storing an entire photo as a giant block of text directly inside a database row (how GateShield currently stores photos). Moving these photos to Amazon S3 makes the database much faster, smaller, and cheaper to back up. |
| Amazon ECS on AWS Fargate | An AWS service that runs packaged software ("Docker containers") automatically without requiring you to manually maintain or patch virtual Linux servers. |
| Amazon RDS for PostgreSQL | AWS's managed PostgreSQL database service that automatically handles database storage, security patching, daily backups, and crash recovery. |
| Amazon S3 (Simple Storage Service) | AWS's secure cloud file storage used to store visitor face photos and scanned ID cards in private, encrypted company folders. |
| ALB (Application Load Balancer) & ACM (AWS Certificate Manager) | The "front door" on AWS that receives HTTPS web traffic, provides the free SSL security padlock (required for mobile/desktop cameras to work in browsers), and sends requests to the GateShield web server. |
| AWS Secrets Manager & AES-256-GCM | AWS's digital vault and bank-grade encryption standard used to lock away database passwords and secret keys so they are never exposed in plain text. |

## Section B: Clear Separation of Completed Work, Partially Completed Work, Planned Multi-Company Features & AWS Deployment Tasks

Before reviewing the detailed phases, this table clearly separates what is already built and working today, what is partially wired, what is pending code work for Multi-Company SaaS, and what is AWS cloud deployment work:

| Status Category | Scope & Items Included | Current Status | Where Covered in This Document |
| --- | --- | --- | --- |
| 1. COMPLETED WORK (Existing Single-Company Product) | • Admin Dashboard & Operator Dashboard (English + Urdu RTL, Light/Dark themes) • Gate-based Operator access restrictions • 6-Step Operator Check-In Wizard & Admin 3-Step Check-In Modal • Pakistani CNIC & Sindh Driving Licence (DLS) OCR scanning + Scanned ID image viewer with zoom/retry • Visitor Card (VC Card No.) active conflict prevention & printable QR Visitor Pass (GKP-...) • Operator QR Login Cards (GKOP_...) with print, regenerate & revoke • Check-Out via QR camera scan or manual search • Employee Portal (self-registration request, status check, login, Special Guest invitation, cancel & re-invite) • Shared Special Guest arrival queue across operators with VC Card No. gate check-in & employee notification • Department management, Employee approval/rejection, Watchlist/Blacklist, Reports & CSV export, Security Audit Logs • Official GateShield branding & gate-opening + perimeter-scanning loader animation | 100% Completed & Working (Single-Company Mode) | Part III (Sections 1–12) & Part II (Section 2) |
| 2. PARTIALLY COMPLETED WORK (In Current Codebase) | • Email Notifications (`src/lib/emailService.ts`): Built and logs to email_outbox, requires production SMTP or Amazon SES credentials (EMAIL_ENABLED=true). • System Settings (`/settings`): Saves company_name, default_visitor_badge_prefix, and auto_checkout_hours to DB, but does not yet dynamically apply them to printed badges or visit numbers. • Department HOD WhatsApp Number: Stored and validated in /departments, but automated WhatsApp message sending on check-in is not implemented. | Partially Implemented | Part II (CHG-09, Section 16) & Part III (Sections 11–12) |
| 3. PENDING / PLANNED CODE FEATURES (Multi-Company SaaS Conversion) | • Central Super Admin Database (`gateshield_central`) & schema (prisma/central.prisma) • Dynamic Tenant Database Manager (`getTenantPrisma(companyId)`) replacing static src/lib/prisma.ts across all 26 API routes • Tenant-Locked Login & JWT Sessions (companyId, companySlug) for Admins, Operators & Employees • Company-Prefixed QR Codes (GKOP_<companySlug>_... & GKP-<companySlug>-...) • Super Admin Owner Console (`/super-admin`) to onboard companies, provision databases, and Activate/Suspend/Deactivate companies • Private Amazon S3 Image Storage (`src/lib/s3Storage.ts`) replacing PostgreSQL Base64 strings • Authentication & Timeout Hardening on /api/scan-cnic, /api/scan-dls, and disabling open public /signup | Planned (Phases 0 to 10) | Part II (Sections 3, 6, 7, 8, 9, 10 & Phases 0–10) |
| 4. PENDING AWS INFRASTRUCTURE & DEPLOYMENT TASKS | • Packaging Next.js (Dockerfile.web) and FastAPI + Pre-baked PaddleOCR models (Dockerfile.ocr) • Setting up AWS VPC, Route 53 DNS, ACM HTTPS certificates, Application Load Balancer (ALB), and ECS Fargate services • Provisioning Amazon RDS PostgreSQL (gateshield_central + company databases) and private Amazon S3 bucket • Migrating existing GateShield database intact as Company #1 • Setting up AWS Secrets Manager, CloudWatch alarms, SNS alerts, and automated RDS + per-company backups | Planned Deployment Tasks (Phases 8, 9, 11 & 12) | Part II (Sections 4, 11, 12, 14, 15 & Phases 8–12) |

# Part II: Complete Multi-Company SaaS Architecture, AWS Deployment & Migration Roadmap

# 1. Executive Summary

GateShield is currently a single-tenant enterprise Visitor & Gate Management System built with Next.js 16.3.6 (App Router), React 19, TypeScript, Prisma 6.19.3, PostgreSQL, and a Python FastAPI + PaddleOCR microservice for Pakistani CNIC and Driving Licence (DLS) extraction.

Today, the entire application connects to a single PostgreSQL database defined by a global singleton PrismaClient (process.env.DATABASE_URL), issues tenant-unaware JWT cookies (gk_token, gk_emp_token), and stores visitor photos and scanned ID card images as Base64 Data URLs directly inside PostgreSQL columns (persons.photoUrl, persons.cnicImageData, persons.dlsImageData, guest_invitations.guestPhotoUrl).

To launch GateShield commercially as a multi-company SaaS product on AWS while meeting your strict requirement of one shared codebase + one independent database per company + one central Super Admin control plane, this roadmap defines a practical evolution:

1. One Shared Next.js + FastAPI Codebase: Deployed as containerized services on Amazon ECS with AWS Fargate behind an Application Load Balancer (ALB).

2. Central Control Plane Database (`gateshield_central`): Hosted on Amazon RDS for PostgreSQL, storing the company registry (companies), company lifecycle status (ONBOARDING, ACTIVE, SUSPENDED, DEACTIVATED), encrypted tenant database connection references, subscription metadata,Super Admin accounts, and platform audit logs.

3. Database-per-Company Isolation (`gateshield_tenant_<slug>`): Each client organization gets its own isolated PostgreSQL database (starting with separate logical databases + separate PostgreSQL credentials on a shared RDS instance for cost efficiency at launch, with seamless graduation to dedicated RDS instances for enterprise tier clients).

4. Dynamic Tenant Prisma Manager (`getTenantPrisma(companyId)`): Replaces the static global prisma import across all 26 tenant API routes with an LRU-cached, connection-limited Prisma client pool bound to the authenticated user's verified companyId.

5. Private Amazon S3 Media Storage (`s3://gateshield-media-prod/<companyId>/...`): Migrates Base64 visitor photos and scanned CNIC/DLS images out of PostgreSQL rows into company-prefixed private S3 prefixes served only via short-lived server-authorized responses or presigned URLs.

# 2. Current Architecture

Based on direct code inspection of the repository, the current GateShield implementation works as follows:

• Frontend & Application Server:

◦ Next.js 16.3.6 App Router (package.json) with client-side pages and server-side API route handlers under src/app/api/**.

◦ Context Providers: AuthContext.tsx (manages current ADMIN/OPERATOR user, currentGate, and theme), LanguageContext.tsx (manages English LTR and Urdu RTL translations), and LayoutContext.tsx (sidebar state).

• Database & Data Access Layer:

◦ Single global PrismaClient initialized from a single DATABASE_URL environment variable.

◦ 10 Models in `prisma/schema.prisma`: User, Gate, UserGateAccess, Person, Visit, Department, AuditLog, SystemSetting, GuestInvitation, AppNotification, and EmailOutbox.

◦ Hybrid Query Pattern: Some routes use Prisma ORM methods (prisma.visit.findMany, prisma.user.findFirst), while Employee Portal, Departments, Document Images, and Email Outbox routes use raw SQL (prisma.$queryRaw and prisma.$executeRaw). Both execute against the same prisma instance.

• Authentication & Authorization (`src/lib/auth.ts`):

◦ Uses jsonwebtoken signed with a single JWT_SECRET and bcryptjs for password hashing.

◦ Staff Cookie (`gk_token`): Stores { id, email, name, role: 'ADMIN' | 'OPERATOR', gateIds }.

◦ Employee Cookies (`gk_emp_token`, `gk_emp_applicant`): Store { id, email, name, role: 'EMPLOYEE', purpose }.

◦ Operator QR Login: Operators can sign in via a printed QR card (GKOP_...) verified against users.qrLoginHash (SHA-256) in src/app/api/auth/qr-login/route.ts.

◦ No Tenant Context: Neither the JWT payload, the users table, nor the login endpoints (/api/auth/login, /api/auth/qr-login, /api/employee/auth/login) include a companyId or company slug.

• OCR Service Integration:

◦ Next.js routes /api/scan-cnic and /api/scan-dls proxy multipart/form-data uploads to process.env.FASTAPI_URL (default http://127.0.0.1:8000/scan-cnic and /scan-dls).

◦ The Python FastAPI service uses PaddleOCR + OpenCV preprocessing to extract text boxes and parse Pakistani CNIC and Sindh Driving Licence fields.

• Visitor Photos & Scanned Document Images:

◦ Client-side utility documentImageCompression.ts compresses images into JPEG/WebP Data URLs.

◦ Stored directly in PostgreSQL TEXT columns (persons.photoUrl, persons.cnicImageData, persons.dlsImageData, guest_invitations.guestPhotoUrl) and served via [/api/visitors/[id]/document-image](file:///d:/Mehmood/cnic-ocr%20system/src/app/api/visitors/%5Bid%5D/document-image/route.ts).

• Email & Notifications (`src/lib/emailService.ts`):

◦ Uses nodemailer configured via global SMTP_* environment variables and records delivery state in the email_outbox table.

◦ In-app notifications (app_notifications) and pending counts use 5–6 second HTTP polling from the browser.

# 3. Desired Multi-Company Architecture

## Visual Traffic & Database Flow (Plain-English Step-by-Step Diagram)

| Step | Component | What Happens in Plain English | Network Zone |
| --- | --- | --- | --- |
| Step 1 | Company Users & Super Admin (Browser / Mobile / Kiosk) | A Company Admin, Gate Operator, or Employee opens GateShield over secure HTTPS (for example, acme.gateshield.com), or the Product Owner opens admin-console.gateshield.com. | Public Internet (HTTPS / TLS 1.3) |
| Step 2 | AWS Application Load Balancer (ALB) + ACM SSL Certificate | Receives all incoming HTTPS traffic, verifies the SSL security certificate (required for browser cameras to scan CNICs and QR codes), and forwards traffic to the GateShield web server container. | AWS Public Subnet |
| Step 3 | GateShield Next.js Web Application (Shared Codebase on ECS Fargate) | Runs one shared codebase for all companies. Reads the user's encrypted login token (JWT), checks which company they belong to, and routes their request. | AWS Private Application Subnet |
| Step 4A | Central Super Admin Database (`gateshield_central` on RDS PostgreSQL) | The web server checks the Central Database to confirm the company is ACTIVE (not suspended) and retrieves the encrypted connection details for that company's database. | AWS Private Isolated Database Subnet |
| Step 4B | Individual Company Databases (`gateshield_tenant_comp_a`, `comp_b`, `comp_c`) | Every company's visitors, visits, employees, gates, departments, and settings are read from and saved to that company's own isolated database only. Company A can never touch Company B's database. | AWS Private Isolated Database Subnet |
| Step 5 | GateShield FastAPI + PaddleOCR Service (Internal Container on Port 8000) | When an operator scans a CNIC or Driving Licence, the Next.js server sends the image over a private internal network to the OCR container, which reads the text in 1–2 seconds and returns it without storing anything. | AWS Private Subnet Only (Never Public) |
| Step 6 | Amazon S3 Private File Storage + AWS Secrets Manager | Visitor photos and scanned ID card images are saved in private company folders (s3://gateshield-media-prod/{companyId}/...). Master passwords and encryption keys are kept locked inside AWS Secrets Manager. | AWS Private Storage Layer |

## Core Architectural Principles

1. Strict Two-Tier Database Separation:

◦ Central Control Plane Database (`gateshield_central`): Accessed via a dedicated centralPrisma client. Holds platform-level data only (Company, CompanyDatabaseConfig, SuperAdminUser, CompanySubscription, PlatformAuditLog, CompanyMetricsSnapshot).

◦ Per-Company Operational Databases (`gateshield_tenant_<slug>`): Each company has its own physical PostgreSQL database containing the existing 10 GateShield operational tables (users, gates, user_gate_access, persons, visits, departments, audit_logs, system_settings, guest_invitations, app_notifications, email_outbox).

2. Trusted Server-Side Tenant Resolution:

◦ Every tenant session token (gk_token, gk_emp_token) embeds { companyId, companySlug, userId, role }.

◦ On every API request, the server verifies the JWT signature, confirms with the cached Central Registry that companyId is ACTIVE (immediately blocking SUSPENDED or DEACTIVATED companies), and resolves the Prisma client for that exact `companyId` only.

◦ Client-supplied query parameters or body fields can never override the JWT's companyId.

3. Scoped Unique Identifiers for QR Codes:

◦ Operator QR login tokens (GKOP_<companySlug>_<random>) and Visitor Pass QR tokens (GKP-<companySlug>-<token>) include the company slug prefix so scanning a card immediately identifies and validates the correct company database and rejects cards belonging to any other company.

# 4. Recommended AWS Architecture

## Component-by-Component AWS Design

| Workload / Layer | Recommended AWS Service | Why This Fits GateShield | Network Visibility |
| --- | --- | --- | --- |
| DNS & Routing | Amazon Route 53 | Supports wildcard tenant subdomains (*.gateshield.com) + admin.gateshield.com. | Public |
| TLS / HTTPS | AWS Certificate Manager (ACM) | Free auto-renewing wildcard TLS certificate (*.gateshield.com). Essential because browser navigator.mediaDevices.getUserMedia (camera OCR & QR scanning) requires HTTPS in production. | Attached to ALB |
| Ingress & Load Balancing | Application Load Balancer (ALB) | Terminates HTTPS, performs health checks (/api/health), and routes traffic to Next.js Fargate tasks. | Public Subnets |
| Main Web & API App | Amazon ECS on AWS Fargate | Runs the stateless Next.js production container (1 vCPU / 2 GB RAM). No EC2 patching required; scales horizontally. | Private Subnets |
| CNIC / DLS OCR Service | Amazon ECS on AWS Fargate (Internal Service via AWS Cloud Map) | Runs the Python FastAPI + PaddleOCR container (2 vCPU / 4 GB RAM) on private port 8000, reachable only by the Next.js ECS security group (http://ocr.gateshield.internal:8000). | Private Subnets Only (Never Public) |
| Relational Databases | Amazon RDS for PostgreSQL (v16) | Hosts gateshield_central and individual company databases (gateshield_tenant_<slug>) with automated backups, encryption at rest (KMS), and SSL/TLS in transit. | Private Isolated DB Subnets |
| Visitor Photos & ID Scans | Amazon S3 (Private Bucket) | Stores visitor face photos and scanned CNIC/DLS images under tenants/<companyId>/photos/ and tenants/<companyId>/id-docs/ with BlockPublicAccess=true and SSE-S3/KMS encryption. | Private (VPC Endpoint) |
| Secrets & Credentials | AWS Secrets Manager | Stores JWT_SECRET, SUPER_ADMIN_JWT_SECRET, RDS master provisioning credentials, and tenant DB encryption keys. Injected via ECS Task Execution Role. | Private |
| Container Registry | Amazon ECR | Private Docker repositories for gateshield-web and gateshield-ocr. | Private |
| Logging & Monitoring | Amazon CloudWatch + SNS | Centralizes Next.js, FastAPI OCR, and RDS logs; triggers SNS email/SMS alerts on high CPU, memory, 5xx errors, or RDS storage pressure. | Internal |
| Automated Backups | AWS Backup + RDS Automated Snapshots | Daily automated RDS snapshots (7–35 day retention) + point-in-time recovery (PITR) + S3 Versioning. | Internal |

## Deep-Dive: Hosting the Python FastAPI + PaddleOCR Workload on AWS

• Why Separate Containerized Service: PaddleOCR loads deep-learning detection and recognition models (PP-OCRv4) into memory and performs CPU-bound OpenCV + inference operations. Running it in a separate ECS Fargate service ensures that a burst of concurrent CNIC scans at multiple company gates never starves the Next.js web server event loop.

• CPU vs GPU Analysis: Standard Pakistani CNIC/DLS card crops are small (~1000×630 px). On a 2 vCPU / 4 GB RAM Linux x86_64 Fargate task (with PaddleOCR CPU inference and enable_mkldnn=True), a single scan takes ~1.2–2.2 seconds without needing an expensive GPU instance (g4dn.xlarge costs ~$380/month, whereas a 2 vCPU / 4 GB Fargate task costs ~$72/month).

• Pre-baked OCR Models in Docker Image: The gateshield-ocr Dockerfile must pre-download the PaddleOCR detection/recognition models during docker build so Fargate tasks start in seconds without downloading models from the internet at runtime.

• One Shared OCR Service Across Companies: The FastAPI OCR service (POST /scan-cnic and POST /scan-dls) is 100% stateless — it receives an image buffer in memory, returns JSON text coordinates, and stores nothing on disk or in a database. Therefore, one shared internal OCR ECS service safely serves all client companies without any tenant data persistence risk.

• Timeouts & Retries: /api/scan-cnic/route.ts and /api/scan-dls/route.ts should enforce an AbortSignal.timeout(15000) (15s timeout) and return a clear retryable status if the OCR container is busy.

# 5. Current vs Desired Architecture Comparison

| Dimension | Current GateShield Architecture (Verified in Code) | Target Multi-Company SaaS Architecture on AWS |
| --- | --- | --- |
| Codebase | Single Next.js + FastAPI repository | Single shared Next.js + FastAPI repository (unchanged principle) |
| Database Topology | Single PostgreSQL database via global src/lib/prisma.ts | 1 Central DB (gateshield_central) + N Company DBs (gateshield_tenant_<slug>) |
| Tenant Resolution | None — all users exist in one shared users table | Subdomain ({slug}.gateshield.com) or Company Code at login + signed companyId inside every JWT |
| Super Admin Layer | None — only company-level ADMIN, OPERATOR, EMPLOYEE roles exist | Dedicated Super Admin auth, central database, and /super-admin Owner Console |
| Operator QR Login | GKOP_<random> looked up in the single users table | GKOP_<companySlug>_<random> routed to the specific company's database |
| Visitor Pass QR | GKP-<random> looked up in the single visits table | GKP-<companySlug>-<random> validated against the active operator's company |
| Photo & ID Storage | Base64 Data URLs stored inside PostgreSQL TEXT columns (persons.cnicImageData, photoUrl) | Private Amazon S3 bucket (tenants/<companyId>/...) with database storing the S3 object key |
| System Settings | Stored in system_settings table in src/app/settings/page.tsx (partially wired) | Stored per-company in each company's system_settings table and enforced dynamically across badges/UI |
| Hosting & HTTPS | Local dev server + ngrok tunnel (next.config.ts) | AWS ALB + ACM HTTPS + ECS Fargate (Next.js + FastAPI OCR) + RDS PostgreSQL |

# 6. Complete List of Required Code Changes

| ID | Area | What Needs to Change & Why | Relevant Existing Files | Layer | Launch Priority | Testing Method |
| --- | --- | --- | --- | --- | --- | --- |
| CHG-01 | Central Prisma & Tenant Prisma Manager | Replace the single global prisma instance with: (1) centralPrisma connected to CENTRAL_DATABASE_URL, and (2) getTenantPrisma(companyId) which looks up the company's encrypted DB connection URL from the Central DB, verifies status === 'ACTIVE', and returns a pooled PrismaClient from a bounded LRU cache (connection_limit=5 per tenant). | src/lib/prisma.ts, new src/lib/centralPrisma.ts, new src/lib/tenantPrisma.ts, prisma/central.prisma | Database / Backend | Mandatory | Unit & concurrency test with 3 tenant DBs under simultaneous requests |
| CHG-02 | Tenant-Aware JWT & Session Resolution | Add companyId and companySlug to AuthUser, EmployeeAuthUser, generateToken(), generateEmployeeToken(), getSessionUser(), and getEmployeeSessionUser(). Query the tenant DB returned by getTenantPrisma(decoded.companyId) instead of the global prisma. | src/lib/auth.ts | Security / Auth | Mandatory | Verify token from Company A is rejected on Company B routes |
| CHG-03 | Company Context in Login & Signup Flows | Resolve company via subdomain ({slug}.gateshield.com) or an explicit Company Code / Workspace ID field on login screens. Disable public unauthenticated /signup (or restrict account creation to company Admins and Super Admin onboarding). | src/app/login/page.tsx, src/app/admin/page.tsx, src/app/employee/page.tsx, src/app/signup/page.tsx, src/app/api/auth/login/route.ts, src/app/api/employee/auth/login/route.ts, src/app/api/employee/auth/register/route.ts | Frontend & Backend Auth | Mandatory | Log in as admin@compA.com and admin@compB.com and verify complete isolation |
| CHG-04 | Tenant-Scoped Operator QR Login & Visitor Pass QR | Prefix Operator QR tokens with GKOP_<companySlug>_<token> and Visitor Pass codes with GKP-<companySlug>-<token> (while keeping backward compatibility for legacy GKOP_ / GKP- tokens mapped to Company #1). | src/lib/operatorQr.ts, src/app/api/auth/qr-login/route.ts, src/app/api/visits/checkout/route.ts | Backend / QR Security | Mandatory | Scan Company A operator/visitor QR on Company B terminal and verify 403 rejection |
| CHG-05 | Update All 26 Tenant API Routes to Use Tenant Prisma | Replace import prisma from '@/lib/prisma' in every tenant API route with const { user, db } = await requireTenantSession() so every Prisma ORM call and every $queryRaw / $executeRaw query runs strictly against that company's database. | All routes under src/app/api/visitors/**, src/app/api/visits/**, src/app/api/gates/**, src/app/api/users/**, src/app/api/departments/**, src/app/api/admin/employees/**, src/app/api/employee/**, src/app/api/reports/**, src/app/api/audit-logs/**, src/app/api/settings/**, src/app/api/blacklist/** | Backend API | Mandatory | Automated API integration test across all endpoints |
| CHG-06 | Super Admin Authentication & Dashboard (`/super-admin`) | Create separate Super Admin login (/super-admin/login), cookie (gs_superadmin_token signed with SUPER_ADMIN_JWT_SECRET), API routes (/api/super-admin/**), and dashboard UI for managing companies, provisioning databases, toggling company status (ACTIVE/SUSPENDED/DEACTIVATED), and viewing health/metrics. | New src/app/super-admin/**, src/app/api/super-admin/**, src/lib/superAdminAuth.ts | Full-Stack (Control Plane) | Mandatory | Verify company ADMIN cannot access /super-admin or /api/super-admin/** |
| CHG-07 | Private S3 Storage for Visitor Photos & ID Images | Replace Base64 storage in PostgreSQL with an S3 service (src/lib/s3Storage.ts) that uploads compressed images to s3://<bucket>/tenants/<companyId>/... and serves them through authenticated routes (/api/visitors/[id]/document-image, /api/visitors/[id]/photo) after verifying the caller's companyId. Keep fallback support for existing Base64 records. | [src/app/api/visitors/[id]/document-image/route.ts](file:///d:/Mehmood/cnic-ocr%20system/src/app/api/visitors/%5Bid%5D/document-image/route.ts), src/app/api/visitors/check-in/route.ts, src/app/api/employee/invitations/route.ts | Backend / Storage | Mandatory for Scale (Can support hybrid Base64 + S3 at launch) | Verify Company A user cannot fetch Company B S3 object key |
| CHG-08 | OCR Proxy Hardening & Auth Check | Require a valid authenticated operator/admin session (getSessionUser()) on /api/scan-cnic and /api/scan-dls (currently unauthenticated!), add a 15-second timeout (AbortSignal.timeout(15000)), and validate file size/MIME before forwarding to FastAPI. | src/app/api/scan-cnic/route.ts, src/app/api/scan-dls/route.ts | Security / OCR | Mandatory | Call /api/scan-cnic without cookie and verify 401 Unauthorized |
| CHG-09 | Enforce Company-Specific Settings Dynamically | Wire system_settings (company_name, default_visitor_badge_prefix, auto_checkout_hours) saved via src/app/settings/page.tsx into visit number/badge prefix generation and printable badge headers so each company sees its own facility name and badge prefix. | src/app/settings/page.tsx, src/components/modals/VisitorBadgeModal.tsx, src/components/modals/OperatorQrCardModal.tsx | Frontend & Backend | Recommended for Launch | Change company_name in Company A settings and verify it appears on Company A badges only |
| CHG-10 | Dockerfiles & Health Check Endpoints | Add /api/health in Next.js and /health in FastAPI for AWS ALB and ECS container health checks; create production Dockerfile.web (Next.js standalone output) and Dockerfile.ocr (Python 3.10 + PaddleOCR pre-downloaded models). | next.config.ts, new src/app/api/health/route.ts, Dockerfile.web, Dockerfile.ocr | Infrastructure / Deployment | Mandatory | Build and run both containers locally and verify health endpoints return 200 OK |

# 7. Central Super Admin Database and Dashboard Plan

## A. What Belongs in the Central Database vs. Company Databases

| Data Category | Central Super Admin DB (gateshield_central) | Individual Company DB (gateshield_tenant_<slug>) |
| --- | --- | --- |
| Super Admin Accounts & MFA/Sessions | Yes (super_admin_users) | No |
| Company Registry & Status (`ONBOARDING`, `ACTIVE`, `SUSPENDED`, `DEACTIVATED`) | Yes (companies) | No |
| Encrypted Tenant DB Connection Details & Schema Version | Yes (company_databases — encrypted with AES-256-GCM using AWS KMS/Secrets Manager key) | No |
| Subscription Plan, Licence Expiry & Max Gates/Users Limits | Yes (company_subscriptions) | No |
| High-Level Aggregated Usage Counters (e.g., total gates, active users, monthly visits count) | Yes (periodic summary snapshot only — zero PII) | Source of truth |
| Platform Audit Trail (company created, suspended, DB migrated) | Yes (platform_audit_logs) | No |
| Company Admins, Operators & Employees (`users`) | No | Yes |
| Visitors, CNIC/DLS Numbers, Photos, Scanned IDs (`persons`) | No | Yes |
| Check-In / Check-Out Logs, Badges, Card Numbers (`visits`) | No | Yes |
| Gates, Gate Assignments, Departments, Invitations | No | Yes |
| Company Security Audit Logs & Email Outbox | No | Yes |

## B. Super Admin Dashboard Features (/super-admin)

### Essential for Commercial Launch (Phase 1 MVP)

• Company Directory & Search: View all registered client organizations with search by company name, slug, or status (ONBOARDING, ACTIVE, SUSPENDED, DEACTIVATED).

• Automated Company Onboarding Wizard ("+ Provision New Company"):

1. Enter Company Name, Slug (acme-corp), Primary Contact, Plan/Expiry, and Initial Company Admin Email & Temporary Password.

2. Automatically creates the isolated PostgreSQL database (gateshield_tenant_acme_corp) and dedicated DB user, runs the Prisma tenant schema migration, seeds the initial Company Admin and default system settings, and marks the company ACTIVE.

• Company Lifecycle Controls: One-click Activate, Suspend (immediately blocks all logins and API calls for that company with a clear "Account Suspended" screen while preserving all data), and Deactivate.

• Tenant Database Health & Migration Status: Displays current schema version, database connectivity check (Healthy / Unreachable), and provisioning status for each company.

• High-Level Usage Summary: Displays count of configured gates, active operators/employees, and total visits for each company without exposing visitor PII.

• Platform Audit Log: Immutable trail of all Super Admin actions (company creation, suspension, credential rotation, schema migration).

### Optional Future Enhancements (Post-Launch Phase 2)

• Automated invoice/billing integration (Stripe) tied to company_subscriptions.

• Self-service tenant custom domain mapping.

• Automated scheduled usage report emails to company owners.

# 8. Company Database Strategy

## Comparing the Two AWS RDS Approaches

| Criterion | Approach 1: Shared RDS PostgreSQL Instance with Separate Logical Databases per Company | Approach 2: Separate RDS PostgreSQL Instance per Company |
| --- | --- | --- |
| How It Works | One RDS PostgreSQL instance hosts gateshield_central, gateshield_tenant_a, gateshield_tenant_b, etc. Each company database has its own distinct PostgreSQL role/username and password with REVOKE CONNECT on all other databases. | Every client company gets its own dedicated AWS RDS PostgreSQL instance (db.t4g.micro or db.t4g.small). |
| Monthly AWS Cost | Low & Predictable: 1 RDS instance ($15–$55/mo) can comfortably host 15 to 40+ small/medium companies at launch. | Linear Cost Multiplication: Every new company adds ~$14–$28/mo minimum in fixed RDS instance + storage costs even when idle. |
| Provisioning Speed | Instant (`~3–8 seconds`): CREATE DATABASE + CREATE ROLE + Prisma schema apply. | Slow (`~5–10 minutes`): Must wait for AWS RDS API CreateDBInstance provisioning. |
| Data & Credential Isolation | Strong: Separate database catalog, separate PostgreSQL user/password, zero shared tables. | Maximum Physical Isolation: Separate VM, separate CPU/RAM/IOPS, independent maintenance windows. |
| Connection Pooling | Requires bounding Prisma connection_limit (e.g., 3–5 per active tenant client) + LRU eviction of idle PrismaClient instances (or RDS Proxy / PgBouncer). | Each instance has its own ~85–200 connection pool limit. |
| Backup & Restore | Instance-level automated RDS snapshots + per-company pg_dump backups to S3 for single-tenant restore. | Native instance-level RDS snapshot restore per company. |

## Recommendation: Hybrid Tiered Strategy (Supported Automatically by Central Registry)

Because our Central Super Admin Database stores the encrypted connection string (dbHost, dbPort, dbName, dbUser, dbPasswordEncrypted) per company:

1. At Launch (Standard Tier Companies): Use Approach 1 (one RDS PostgreSQL instance hosting separate databases and separate PostgreSQL credentials per company). This keeps your baseline AWS bill low and allows 5-second company onboarding.

2. Enterprise Tier / High-Volume Companies: Because getTenantPrisma(companyId) connects using the host stored in that company's Central DB record, if a large enterprise or government client requests a dedicated physical RDS instance (Approach 2), you simply point their company_databases record to their dedicated RDS endpoint — with zero code changes!

# 9. OCR and File Storage Strategy

## A. Migrating Visitor Photos & Scanned ID Cards to Private Amazon S3

Currently, persons.photoUrl, persons.cnicImageData, and persons.dlsImageData store full Base64 strings (~80 KB – 450 KB per image) directly inside PostgreSQL rows. Across thousands of visitors and multiple companies, this inflates RDS storage, slows backups, and increases memory pressure.

Recommended S3 Architecture:

• Create a single private S3 bucket (gateshield-media-prod) with Block All Public Access = ON and Default Encryption (SSE-S3 or KMS) = ON.

• Enforce strict company key prefixes:

◦ Visitor Face Photos: tenants/{companyId}/persons/{personId}/photo-{timestamp}.jpg

◦ Scanned CNIC Images: tenants/{companyId}/persons/{personId}/cnic-{timestamp}.jpg

◦ Scanned DLS Images: tenants/{companyId}/persons/{personId}/dls-{timestamp}.jpg

◦ Invited Guest Photos: tenants/{companyId}/invitations/{invitationId}/photo-{timestamp}.jpg

• Backward-Compatible Retrieval:

◦ In [/api/visitors/[id]/document-image/route.ts](file:///d:/Mehmood/cnic-ocr%20system/src/app/api/visitors/%5Bid%5D/document-image/route.ts), if cnicImageData starts with s3:// or tenants/, verify that the key starts with tenants/${user.companyId}/, fetch the object stream from S3, and return it with Cache-Control: private, no-store. If it starts with data:image/, serve the legacy Base64 data URL as today.

# 10. Security and Isolation Assessment

| Threat Vector | How the Target Architecture Prevents It |
| --- | --- |
| 1. Cross-Company API Manipulation (IDOR) | Every API route resolves its database connection exclusively from session.companyId inside the verified httpOnly JWT cookie — never from URL params or request bodies. Even if an attacker in Company A sends a valid personId or visitId from Company B, the query executes against Company A's database, where that ID does not exist (404 Not Found). |
| 2. Cross-Company Concurrent Request Bleed | Never store the active tenant on a mutable global variable. Instead, getTenantPrisma(companyId) is a pure function keyed by companyId returning an isolated PrismaClient instance bound to that company's database URL. |
| 3. Company Admin Attempting Super Admin Access | Super Admin uses a separate cookie (gs_superadmin_token), signed with a separate secret (SUPER_ADMIN_JWT_SECRET), and verified against super_admin_users in gateshield_central. Company ADMIN tokens are rejected by /api/super-admin/**. |
| 4. Suspended Company Continuing Operations | A lightweight in-memory TTL cache (e.g., 15-second TTL, immediately invalidated when Super Admin clicks Suspend) checks company.status === 'ACTIVE' on every authenticated request. Suspended companies immediately receive 403 Company Suspended. |
| 5. Cross-Company Cache Contamination | All dynamic API routes return Cache-Control: private, no-store, and any server-side caches (such as active department lists or company status) are keyed by ${companyId}:${resourceKey}. |
| 6. Database Credential Exposure | Tenant database passwords are never returned to the frontend or even to the Super Admin browser UI; they are encrypted at rest in gateshield_central using an encryption key stored in AWS Secrets Manager. |
| 7. Private S3 File Leakage | S3 bucket has public access blocked. Server-side image endpoints verify that the requested S3 key begins with tenants/${session.companyId}/ before reading from S3. |

# 11. Data Migration Plan (Preserving Existing Product Data as Company #1)

Your current GateShield installation and all existing records (Admins, Operators, Employees, Gates, Departments, Visitors, Visits, Scanned IDs, Invitations, and Audit Logs) will become Company #1 without data loss:

1. Step 1 — Full Pre-Migration Backup:

◦ Run pg_dump -Fc --no-acl --no-owner -d <current_db_url> -f gateshield_pre_saas_backup.dump and verify restoration into a temporary local/staging database.

2. Step 2 — Provision AWS RDS & Create `gateshield_central`:

◦ Create the RDS PostgreSQL instance in private subnets.

◦ Create the gateshield_central database and apply prisma/central.prisma migrations.

◦ Seed your Super Admin Owner account in gateshield_central.

3. Step 3 — Provision Company #1 Database (`gateshield_tenant_default`):

◦ Create the isolated database gateshield_tenant_<company1_slug> and its dedicated PostgreSQL user on RDS.

◦ Restore gateshield_pre_saas_backup.dump directly into gateshield_tenant_<company1_slug>.

◦ Register Company #1 in gateshield_central.companies (status = 'ACTIVE') with its encrypted connection reference.

4. Step 4 — Optional S3 Media Migration Script:

◦ Because our S3 retrieval helper supports both legacy data:image/... strings and tenants/<companyId>/... S3 keys, existing visitors' photos and scanned CNIC/DLS images work immediately on Day 1. A background script can optionally upload existing Base64 images to S3 and replace the column values with S3 keys with zero downtime.

5. Step 5 — Verification & Rollback Plan:

◦ Verify record counts (users, gates, departments, persons, visits, guest_invitations) in gateshield_tenant_<company1_slug> match the source database 100%.

◦ Keep the original database intact in read-only standby during cutover so DNS/traffic can be switched back immediately if needed.

# 12. AWS Deployment and Release Strategy

## Step-by-Step Safe Release & Deployment Flow on AWS

| Stage | Action | Plain-English Explanation |
| --- | --- | --- |
| Stage 1: Git Push / Release Tag | Developer pushes verified update to the single shared GateShield repository. | One code update prepares improvements for all client companies at once. |
| Stage 2: Automated Quality Checks (CI/CD) | Runs TypeScript check (tsc --noEmit), linting, and container build. | Stops any broken code before it can reach staging or production. |
| Stage 3: Push Docker Images to Amazon ECR | Uploads gateshield-web (Next.js) and gateshield-ocr (FastAPI PaddleOCR) images to AWS's private container registry. | Stores versioned, ready-to-run application packages privately on AWS. |
| Stage 4: Staging Deployment & Canary Test | Deploys the update to a Staging environment and runs database updates on a test company database first. | Confirms the database update works safely before touching any real customer database. |
| Stage 5: Coordinated Company DB Migration | Runs the database update script across each company's database (Canary DB first, then all active company DBs). | Keeps every company's database structure in sync with the shared codebase. |
| Stage 6: Zero-Downtime ECS Fargate Rollout | Starts the new application containers, waits for /api/health to pass, and smoothly switches traffic over. | Gate operators and employees experience zero downtime during product updates. |

## Safe Schema Migrations Across Multiple Company Databases

When you add a new feature to the shared codebase that requires a database column or table change:

1. Backward-Compatible Migrations First (Expand/Contract Pattern): New columns should be nullable or have defaults so the currently running container remains compatible while migrations run.

2. Centralized Tenant Migration Runner: A Super Admin CLI/script queries gateshield_central for all companies, runs prisma migrate deploy (or idempotent SQL migration files) against a Canary/Staging company DB first, and only proceeds across remaining company databases if the canary succeeds.

3. Per-Company Schema Version Tracking: gateshield_central.company_databases records schemaVersion and lastMigratedAt for every company so the Super Admin Dashboard shows at a glance that all companies are on the latest schema.

# 13. Phased Implementation Roadmap

## Phase 0: Codebase, Security & Infrastructure Audit

• Objectives: Lock down unauthenticated endpoints (such as /api/scan-cnic, /api/scan-dls, and public /signup) and finalize environment variable contracts.

• Required Changes: Add session checks to OCR proxy routes; prepare .env.example template for multi-tenant mode.

• Prerequisites: Existing codebase.

• Deliverables: Hardened API baseline.

• Dependencies: None.

• Relative Complexity: Low.

• Major Risks: Leaving /signup open in production could let unauthorized users create accounts.

• Acceptance Criteria: All API routes require appropriate authentication; npx tsc --noEmit passes.

## Phase 1: Final Multi-Tenant & AWS Architecture Design

• Objectives: Finalize tenant routing mode (subdomain {company}.gateshield.com + fallback Company Code input on login), AWS VPC subnet layout, and RDS sizing.

• Required Changes: None (design & AWS account preparation).

• Prerequisites: Domain name registered in Route 53 or external DNS.

• Deliverables: AWS VPC, security groups, and IAM role specifications.

• Dependencies: Phase 0.

• Relative Complexity: Low.

• Major Risks: Misconfigured NAT Gateway or public RDS exposure.

• Acceptance Criteria: Architecture and network security rules signed off.

## Phase 2: Backup, Migration & Recovery Tooling

• Objectives: Build repeatable backup, restore, and tenant database provisioning scripts.

• Required Changes: Create script to dump existing DB, create a new PostgreSQL tenant DB + isolated DB role, and apply tenant schema.

• Prerequisites: PostgreSQL client tools.

• Deliverables: Verified backup/restore and tenant DB provisioning utility.

• Dependencies: Phase 1.

• Relative Complexity: Low–Medium.

• Major Risks: Incomplete schema creation for raw SQL tables (departments, guest_invitations, app_notifications, email_outbox) if relying only on older SQL scripts — must use unified prisma/schema.prisma.

• Acceptance Criteria: Provisioning script creates a clean tenant DB with all 10 tables in under 10 seconds.

## Phase 3: Central Super Admin Database & Authentication

• Objectives: Introduce prisma/central.prisma, centralPrisma client, and Super Admin authentication (gs_superadmin_token).

• Required Changes: Add Central DB schema (Company, CompanyDatabaseConfig, SuperAdminUser, PlatformAuditLog), AES-256-GCM credential encryption helper, and /api/super-admin/auth/**.

• Prerequisites: Phase 2.

• Deliverables: Working Central DB and Super Admin login backend.

• Dependencies: Phase 2.

• Relative Complexity: Medium.

• Major Risks: Storing plaintext tenant DB passwords (mitigated via AES-256-GCM encryption).

• Acceptance Criteria: Super Admin can authenticate; tenant users cannot use Super Admin endpoints.

## Phase 4: Company Registry & Automated Onboarding Service

• Objectives: Build the backend provisioning service that registers a new company in gateshield_central, creates its isolated PostgreSQL database, applies the tenant schema, and seeds its initial Admin user and default gate.

• Required Changes: New src/lib/companyProvisioner.ts and /api/super-admin/companies endpoints.

• Prerequisites: Phase 3.

• Deliverables: End-to-end automated company database creation API.

• Dependencies: Phase 3.

• Relative Complexity: Medium–High.

• Major Risks: Partial provisioning if DB creation succeeds but schema apply fails (mitigated by recording PROVISIONING_FAILED status and supporting safe retry).

• Acceptance Criteria: Calling the onboarding service creates a new isolated company DB and seeds its initial Admin account.

## Phase 5: Dynamic Tenant Database Routing (getTenantPrisma)

• Objectives: Replace the static single-DB Prisma import with dynamic, bounded per-company Prisma client resolution across all 26 tenant API routes.

• Required Changes: Implement src/lib/tenantPrisma.ts (with LRU cache, max idle eviction, and connection_limit=5) and update all tenant API routes.

• Prerequisites: Phase 4.

• Deliverables: Multi-database routing layer across all Visitor, Gate, Department, Employee, Special Guest, Report, and Audit routes.

• Dependencies: Phase 4.

• Relative Complexity: High.

• Major Risks: Missing a route that still imports the old global prisma (mitigated by removing default single-DB fallback in multi-tenant mode).

• Acceptance Criteria: Zero tenant API routes reference a global tenant-unaware PrismaClient.

## Phase 6: Role, Login & QR Code Multi-Company Adaptation

• Objectives: Embed companyId and companySlug into Admin, Operator, and Employee sessions, login screens, Operator QR cards, and Visitor Pass QR codes.

• Required Changes: Update src/lib/auth.ts, src/lib/operatorQr.ts, /api/auth/login, /api/auth/qr-login, /api/employee/auth/login, and login UIs.

• Prerequisites: Phase 5.

• Deliverables: Tenant-scoped authentication for all 3 user roles (ADMIN, OPERATOR, EMPLOYEE) + QR codes.

• Dependencies: Phase 5.

• Relative Complexity: Medium.

• Major Risks: Breaking legacy QR cards for Company #1 (mitigated by routing unprefixed legacy GKOP_ tokens to Company #1).

• Acceptance Criteria: Users with identical emails in Company A and Company B log into their respective isolated companies without conflict.

## Phase 7: Super Admin Dashboard UI (/super-admin)

• Objectives: Build the owner-only Super Admin web console.

• Required Changes: Create /super-admin pages for company list, search/filter, "+ Provision New Company" modal, Activate/Suspend/Deactivate actions, DB health check, usage summary metrics, and platform audit logs.

• Prerequisites: Phase 4 & Phase 6.

• Deliverables: Complete Super Admin Dashboard UI.

• Dependencies: Phases 4, 6.

• Relative Complexity: Medium.

• Major Risks: Accidental suspension of an active company (mitigated by confirmation dialog).

• Acceptance Criteria: Product owner can onboard, inspect, suspend, and reactivate companies from the browser.

## Phase 8: OCR Containerization & Private S3 File Storage

• Objectives: Move visitor photo and scanned ID storage to private Amazon S3 (tenants/<companyId>/...) and containerize both Next.js and FastAPI PaddleOCR services.

• Required Changes: Implement src/lib/s3Storage.ts, update image endpoints, and create Dockerfile.web and Dockerfile.ocr.

• Prerequisites: Phase 5.

• Deliverables: Production Docker images and S3-backed media storage.

• Dependencies: Phase 5.

• Relative Complexity: Medium.

• Major Risks: PaddleOCR downloading models at runtime (mitigated by baking models into Dockerfile.ocr).

• Acceptance Criteria: Photos and ID scans upload to private S3 under company prefixes and render only for authorized users of that company.

## Phase 9: Data Migration of Existing Installation (Company #1)

• Objectives: Migrate your existing GateShield database into the first tenant database (gateshield_tenant_<company1>) on staging/production RDS.

• Required Changes: Execute backup/restore and register Company #1 in gateshield_central.

• Prerequisites: Phases 5–8.

• Deliverables: Existing installation running intact as Company #1.

• Dependencies: Phases 5–8.

• Relative Complexity: Medium.

• Major Risks: Missing historical images or active visits (mitigated by post-migration row-count and checksum verification).

• Acceptance Criteria: All existing Admins, Operators, Employees, Gates, Departments, and Visits work identically under Company #1.

## Phase 10: Multi-Tenant Security & Regression Testing

• Objectives: Execute full cross-tenant penetration tests and functional regression suite.

• Required Changes: Run automated and manual checklist (Section 15).

• Prerequisites: Phase 9.

• Deliverables: Signed-off QA & security test report.

• Dependencies: Phase 9.

• Relative Complexity: Medium.

• Major Risks: Edge-case leakage in raw SQL queries (verified by testing every endpoint with cross-company tokens).

• Acceptance Criteria: 100% pass rate on all mandatory launch tests in Section 15.

## Phase 11: AWS Staging, Production Deployment, DNS & HTTPS Setup

• Objectives: Deploy ECR images to ECS Fargate, configure ALB + ACM HTTPS certificate, Route 53 DNS, Secrets Manager, and private S3 VPC endpoints.

• Required Changes: AWS infrastructure provisioning.

• Prerequisites: Phase 10.

• Deliverables: Live HTTPS production environment on AWS.

• Dependencies: Phase 10.

• Relative Complexity: Medium.

• Major Risks: Browser camera blocked if HTTPS is misconfigured (verified via ACM TLS on ALB).

• Acceptance Criteria: Mobile and desktop browsers can open camera for CNIC OCR and QR scanning over HTTPS.

## Phase 12: Monitoring, Automated Backups, Disaster Recovery & Launch

• Objectives: Enable CloudWatch alarms, SNS alerts, RDS automated snapshots + per-tenant backup job, and onboard first commercial client companies.

• Required Changes: CloudWatch metric alarms and AWS Backup rules.

• Prerequisites: Phase 11.

• Deliverables: Production-ready commercial SaaS platform.

• Dependencies: Phase 11.

• Relative Complexity: Low.

• Major Risks: Unnoticed disk fill or OCR task crash (mitigated by CloudWatch alarms + ECS auto-restart).

• Acceptance Criteria: Simulated container crash and DB snapshot restore tested successfully.

# 14. Cost Drivers and Indicative AWS Scenarios

Pricing research date: October 2026, based on official AWS On-Demand pricing for US East (`us-east-1`) / Asia Pacific (`ap-south-1`, ~5–8% variance), 730 hours/month continuous operation.

## Main AWS Cost Drivers

1. ECS Fargate Compute: Particularly the FastAPI + PaddleOCR service (1–2 vCPU / 2–4 GB RAM), which needs enough RAM to hold PaddleOCR models in memory.

2. RDS PostgreSQL Instance & Storage: Single-AZ vs. Multi-AZ and instance size (db.t4g.small vs db.t4g.medium).

3. Application Load Balancer (ALB) & Networking: Fixed hourly ALB cost (~$16.43/mo + LCU usage). Tip: Use an S3 Gateway VPC Endpoint (free) and ECR VPC Endpoints or public subnet w/ security group bloquear to avoid a `$32/mo` NAT Gateway in early launch.

## Three Indicative Monthly Cost Scenarios

| AWS Resource | Scenario A: Early Commercial Launch (1–5 Companies, ~200 visits/day) | Scenario B: Growing SaaS (10–25 Companies, ~1,500 visits/day) | Scenario C: High-Availability Scale (50+ Companies, Multi-AZ) |
| --- | --- | --- | --- |
| RDS PostgreSQL (Hosting Central DB + Isolated Tenant DBs) | 1× db.t4g.small (2 vCPU, 2 GB RAM, Single-AZ, 30 GB gp3): ~$27 / mo | 1× db.t4g.medium (2 vCPU, 4 GB RAM, Single-AZ, 100 GB gp3): ~$60 / mo | 1× db.m7g.large (2 vCPU, 8 GB RAM, Multi-AZ, 250 GB gp3): ~$235 / mo |
| ECS Fargate — Next.js App (`gateshield-web`) | 1× Task (0.5 vCPU / 1 GB RAM): ~$18 / mo | 2× Tasks (1 vCPU / 2 GB RAM each, auto-scaled): ~$72 / mo | 3× Tasks (1 vCPU / 2 GB RAM each): ~$108 / mo |
| ECS Fargate — FastAPI + PaddleOCR (`gateshield-ocr`) | 1× Task (1 vCPU / 2 GB RAM): ~$36 / mo | 2× Tasks (2 vCPU / 4 GB RAM each): ~$144 / mo | 3× Tasks (2 vCPU / 4 GB RAM each): ~$216 / mo |
| Application Load Balancer (ALB) + ACM TLS | 1× ALB + low LCU traffic (ACM TLS is free): ~$22 / mo | 1× ALB + moderate LCU traffic: ~$28 / mo | 1× ALB + higher LCU traffic: ~$42 / mo |
| Amazon S3 (Private Visitor Photos & Scanned IDs) | 25 GB storage + requests: ~$1 / mo | 150 GB storage + requests: ~$5 / mo | 500 GB storage + requests: ~$14 / mo |
| Secrets Manager, ECR, Route 53 & CloudWatch Logs | 5 secrets + 1 hosted zone + 5 GB logs: ~$6 / mo | 10 secrets + 15 GB logs + backups: ~$16 / mo | Secrets + 40 GB logs + RDS PITR backups: ~$45 / mo |
| Estimated Monthly AWS Total | ~$110 USD / month | ~$325 USD / month | ~$660 USD / month |

## Cost Optimization Option for Ultra-Lean Initial Launch

If you want to launch for the first 1–3 client companies at the lowest possible monthly cost (~$60–$70/month) without sacrificing database isolation or S3 privacy:

• Run both containers (gateshield-web and gateshield-ocr) via Docker Compose on a single Amazon EC2 `t3.medium` (2 vCPU, 4 GB RAM, ~$30/mo) in a public subnet with an Application Load Balancer (or CloudFront + ACM) in front of it, connected to a private RDS PostgreSQL `db.t4g.small` (~$27/mo) hosting gateshield_central and each company's separate PostgreSQL database, plus Amazon S3 (~$1/mo). When you grow past 5–8 companies, move the identical Docker images onto ECS Fargate with zero code changes.

# 15. Testing and Launch Checklist

Every item marked [MANDATORY FOR LAUNCH] must pass before onboarding paying client organizations:

## A. Multi-Company Isolation & Security Tests

☐ [MANDATORY FOR LAUNCH] Simultaneous Multi-Company Operations: Two operators logged into Company A and Company B simultaneously register visitors, assign VC-01, and check out visitors — both succeed without card conflict because VC-01 is validated only within each company's own database.

☐ [MANDATORY FOR LAUNCH] Identical User Emails Across Companies: admin@company.com or guard1@facility.com can exist independently in Company A's database and Company B's database with separate passwords and permissions.

☐ [MANDATORY FOR LAUNCH] Cross-Company IDTampering (IDOR): Using a valid Company A gk_token cookie, request /api/visitors/<companyB_personId>, /api/visitors/<companyB_personId>/document-image?type=cnic, and /api/visits/<companyB_visitId> — all must return 404 Not Found or 403 Forbidden.

☐ [MANDATORY FOR LAUNCH] Cross-Company QR Scan Rejection: Scanning a Company A Operator QR card (GKOP_compA_...) or Visitor Pass QR (GKP-compA-...) on a Company B terminal is rejected with 403 Forbidden.

☐ [MANDATORY FOR LAUNCH] Super Admin Boundary Check: A logged-in Company ADMIN attempting to access /super-admin or /api/super-admin/companies receives 401/403.

☐ [MANDATORY FOR LAUNCH] Company Suspension Enforcement: When Super Admin changes Company B's status to SUSPENDED, active Admins, Operators, and Employees in Company B are blocked from performing any check-in, invitation, or data fetch within 15 seconds.

## B. Database Provisioning, Migration & Resilience Tests

☐ [MANDATORY FOR LAUNCH] Automated Company Onboarding: Creating a new company from the Super Admin Dashboard provisions its PostgreSQL database, runs all table migrations, and creates its initial Admin account in one workflow.

☐ [MANDATORY FOR LAUNCH] Connection Pool Ceiling Test: Simulate 15 active companies making concurrent API requests and verify the LRU PrismaClient pool stays comfortably below the RDS PostgreSQL max_connections limit.

☐ [MANDATORY FOR LAUNCH] Isolated Database Failure Handling: If one company's database credentials are revoked or unreachable, requests for that company return a clean 503 Service Unavailable error while all other companies continue operating normally.

☐ [MANDATORY FOR LAUNCH] Coordinated Schema Migration & Rollback: Test applying a new Prisma migration across 3 staging tenant databases and verify rollback procedure if one database fails.

## C. Core Product Regression & AWS Infrastructure Tests

☐ [MANDATORY FOR LAUNCH] End-to-End Visitor Check-In & Check-Out: Verify both the Operator 6-step wizard and Admin 3-step modal across all 6 categories (VISITOR, VENDOR, INTERVIEW, SPECIAL_GUEST, CONTRACTOR, DELIVERY).

☐ [MANDATORY FOR LAUNCH] HTTPS Camera Access & CNIC/DLS OCR: On both mobile (iOS Safari / Android Chrome) and desktop over the production HTTPS domain, verify live camera capture and OCR extraction for CNIC and Driving Licence cards.

☐ [MANDATORY FOR LAUNCH] Employee Portal & Special Guest Flow: Employee self-registration, Admin approval, Employee login, Guest invitation creation, Operator real-time arrival alert, VC Card No. assignment at gate, and Employee check-in notification.

☐ [MANDATORY FOR LAUNCH] Private S3 Photo & ID Document Security: Verify direct unauthenticated S3 URLs return 403 Access Denied, while /api/visitors/[id]/document-image renders the image strictly for authenticated staff of the owning company.

☐ [MANDATORY FOR LAUNCH] Backup & Single-Company Restore Drill: Restore a single company's database backup into a test database and verify 100% of visits, users, and S3 image links resolve properly.

# 16. Risks, Dependencies, and Unresolved Decisions

## Key Technical Risks to Manage During Implementation

1. PostgreSQL Connection Exhaustion on Shared RDS:

◦ Risk: Each PrismaClient opens a default connection pool (num_cpus * 2 + 1). Creating 30 unbounded PrismaClient instances in one Next.js process would open 150+ connections and exhaust a small RDS instance.

◦ Mitigation: Always append ?connection_limit=3&pool_timeout=10 to each tenant database URL in getTenantPrisma(companyId) and evict/disconnect idle PrismaClient instances after 10 minutes of inactivity using an LRU cache.

2. Raw SQL Queries Bypassing Prisma Models:

◦ Risk: Several existing GateShield features (Employee Portal, Invitations, Departments, Email Outbox, Document Images) use prisma.$queryRaw and prisma.$executeRaw.

◦ Mitigation: Because every company has its own separate PostgreSQL database, routing db.$queryRaw through the tenant's own PrismaClient instance (const { db } = await requireTenantSession()) automatically isolates all raw SQL queries to that company's database without needing to rewrite every SQL query to add WHERE company_id = ....

3. Unauthenticated OCR Proxy Endpoints:

◦ Risk: Currently, /api/scan-cnic and /api/scan-dls do not call getSessionUser(). If exposed on the public internet, external bots could abuse your OCR compute.

◦ Mitigation: Add getSessionUser() authentication and file size limits to both routes in Phase 0.

## Decisions to Confirm Before Starting Implementation

1. Tenant URL / Login Style:

◦ Option 1 (Recommended): Company Code / Workspace Slug on Login (gateshield.com/login with a Company Code field, plus optional direct links like gateshield.com/login?company=acme) OR Subdomain Routing (acme.gateshield.com). Supporting both (auto-detecting subdomain when present, and showing a Company ID field on the main domain) gives the best UX for both factory kiosks and mobile employees.

2. AWS Region Selection:

◦ Choose the region closest to your target customers for lowest camera-upload and OCR latency: Middle East (UAE `me-central-1`) or Asia Pacific (Mumbai `ap-south-1`) (~35–60ms latency from Pakistan).

3. Email Sending Service in Production:

◦ For reliable delivery of Employee approval/registration emails on AWS, use Amazon SES (Simple Email Service) via src/lib/emailService.ts ($0.10 per 1,000 emails).

# 17. Recommended First Step

Start with Phase 0 + Phase 3 & 5 (Core Multi-Database Foundation) locally before provisioning paid AWS resources:

1. Introduce `prisma/central.prisma` and `src/lib/tenantPrisma.ts`:

◦ Set up the gateshield_central database and the getTenantPrisma(companyId) connection manager locally with two test company databases (gateshield_tenant_alpha and gateshield_tenant_beta).

2. Update `src/lib/auth.ts` and the Login Endpoints:

◦ Embed companyId and companySlug into the JWT session cookies and route all API requests through getTenantPrisma(session.companyId).

3. Build the `/super-admin` Onboarding Console:

◦ Verify that you can create a new company from /super-admin, have its isolated PostgreSQL database provisioned automatically, and log into both companies side-by-side with complete data isolation.

# Part III: Complete Baseline Inventory of Existing GateShield Features (Completed Work in Current Application)

The following 12 sections document every feature, screen, button, modal, workflow, and status note currently implemented in the GateShield codebase. All of these capabilities will be preserved for every client company in the multi-company SaaS architecture:

## 1. Admin Dashboard

• Sidebar Navigation Menu (Dashboard, Visitors, Vendors, Interviews, Special Guests, Contractors, Deliveries, Departments, Employees, Reports & Analytics, Audit Logs, Manage Access, Settings)

• Collapse / Expand Desktop Sidebar Button

• Mobile Navigation Drawer (Open Menu / Close Menu)

• Pending Employee Requests Badge Counter (on Employees sidebar link)

• Active Gate Selector Dropdown (All Gates or individual gates)

• Live Clock and Current Date Badge (12-hour AM/PM format)

• Quick Action Buttons:

◦ Check-Out / Scan Exit button

◦ + Register Entry button

• Summary Metric Cards:

◦ Currently Inside counter

◦ Entries Today counter

◦ Checked Out Today counter

◦ Active Gates counter

• Category Breakdown Counter Cards (Visitors, Vendors, Interviews, Special Guests, Contractors, Deliveries)

• Active Visitors Inside Table:

◦ Search input (Search active visitors by name, CNIC, card #, host...)

◦ Visitor profile link, category badge, host & department, VC card number, entry gate & check-in time

◦ View Details action button (opens Visitor Details Modal with scanned ID card images)

◦ Print Badge action button

◦ Checkout action button

◦ Delete Visit Record action button (with confirmation dialog)

• Recent Activity Feed (latest check-ins and check-outs with status and time)

• Theme Toggle Button (Light / Dark)

• Logout Button

## 2. Operator Dashboard

• Assigned Gate Indicator / Selector:

◦ Automatic lock to assigned gate (when assigned to 1 gate)

◦ Assigned gates dropdown selector (when assigned to multiple gates)

◦ No Gate Assigned warning banner (when no gate is assigned)

• Language Switcher Toggle (English / اردو)

• Theme Toggle Button (Light / Dark)

• Live Clock and Current Date Badge (12-hour AM/PM format)

• Main Operator Action Tiles (4 Primary Actions):

◦ Register tile (opens 6-step visitor registration wizard)

◦ Check-Out tile (opens visitor check-out modal)

◦ Special Guest tile with live pending guest count badge (opens Special Guest List modal)

◦ Search / Inside tile (opens active inside visitors search & check-out view)

• Real-Time Invited Guest Arrival Toast Alert:

◦ Audio alert chime on new employee guest invitation

◦ Open List quick action button

◦ Dismiss button

• Logout Button

## 3. Employee Portal

• Employee Portal Login Tab (Email Address, Password, Sign In to Portal button)

• Employee Registration Request Tab:

◦ Full Name input

◦ Department dropdown (active departments)

◦ Position / Designation input

◦ Phone Number input

◦ Email Address input

◦ Password and Confirm Password inputs

◦ Submit Registration Request button

• Check Approval Status Lookup:

◦ Check Request Status by email input

◦ Displays PENDING, APPROVED, or REJECTED status (with rejection reason if provided)

• Employee Header Bar:

◦ Employee name, department badge, and position display

◦ In-app notifications bell counter and notification list

◦ Mark All Read notifications button

◦ Refresh button

◦ Theme Toggle button (Light / Dark)

◦ Logout button

• Invite Guest Tab (`Invite a Special Guest` Form):

◦ Guest Full Name input

◦ Guest Phone Number input (03XXXXXXXXX / +923XXXXXXXXX validation)

◦ Guest CNIC Number input (optional, auto-formatted XXXXX-XXXXXXX-X)

◦ Visit Date picker

◦ Arrival Time picker

◦ Visit Duration selector (15 Minutes, 30 Minutes, 45 Minutes, 1 Hour, 2 Hours, Half Day (4 Hours), Full Day (8 Hours))

◦ Guest Photo upload (optional, with preview and Remove Photo button)

◦ Send Guest Invitation submit button

• Visited Guests / Invitation History Tab:

◦ Search input (Search by guest name, phone, CNIC, or card #...)

◦ Status filter pills (All, Pending, Checked In, Checked Out, Cancelled)

◦ Guest invitation records table (Guest, Visit Date & Arrival Time, VC Card No., Gate & Check-In / Out Time, Status, Actions)

◦ Cancel Invitation button (for Pending invitations)

◦ Re-invite button (opens Re-invite: {Guest Name} modal with pre-filled guest details and new date/time selection)

## 4. Visitor Management

• Category Registry Pages:

◦ All Registered Visitors (/visitors)

◦ Vendors (/vendors)

◦ Interviews (/interviews)

◦ Special Guests (/special-guests)

◦ Contractors (/contractors)

◦ Deliveries (/deliveries)

• Registry Filter Bar:

◦ Search input (Search by Name, CNIC, Phone, Card #, Host...)

◦ Gate filter dropdown (All Gates for Admin; assigned gates for Operator)

◦ Status filter dropdown (All Statuses, Currently Inside, Checked Out)

◦ Date filter picker (Filter date + Clear date button)

• Registry Actions:

◦ Export CSV button

◦ + Register Entry button

◦ Print Badge row button

◦ History row button (opens Person Profile & History page)

◦ Exit row button (for INSIDE visitors)

◦ Delete Record row button (Admin only, with confirmation modal)

◦ Pagination controls (Previous Page, Next Page)

• Person Profile & History Page (`/person/[id]`):

◦ Back to Visitor Registry link

◦ Visitor photo, full name, father/husband name, category, CNIC, Driving Licence number, phone number, gender, date of birth, issue/expiry dates, licensing authority, identification mark, company, present/permanent address, carried belongings, and lifetime visit count

◦ ☆ Mark as VIP / ★ VIP Marked toggle button

◦ Blacklist / Unblacklist Person button (with blacklist reason modal)

◦ Delete person profile button (Admin only, with confirmation modal)

◦ Scanned ID Card Images section (CNIC and Driving Licence image cards, Expand / Zoom lightbox modal, Retry button if image fails to load)

◦ Visit History Logs table (visit number, host & department, card #, check-in/out times, duration, status, Print Badge button, and Admin Delete Visit button)

## 5. Special Guest Management

• Special Guest List Modal (`Special Guest List` / `مہمانوں کی فہرست`):

◦ Total waiting guests count badge

◦ Search input (Search by guest name, host employee, department, phone, or CNIC...)

◦ Refresh button

◦ Guest cards displaying:

▪ Guest photo or avatar

▪ Guest name, phone number, and CNIC (if provided)

▪ Inviting employee name and department

▪ Visit Date, Arrival Time, and Visit Duration

▪ Early / On-Time / Late arrival status indicator (allows check-in even if guest arrives outside the estimated time slot)

▪ Select & Assign Card button

• Special Guest Gate Check-In Popup:

◦ Full guest and host employee summary

◦ Active gate display

◦ VC Card No. input field (required at gate check-in, with live duplicate/active card check)

◦ Confirm Check-In button

◦ Automatic removal of guest from Pending list across all operator terminals after check-in

• Post Check-In Success Modal:

◦ Displays assigned VC Card No., visit number, guest name, host, and department

◦ View Card button (opens Visitor Pass / Badge preview)

◦ Print Badge button (opens printable Visitor Pass and triggers print)

◦ Done button

## 6. CNIC and Driving Licence Scanning

• Document Type Selection:

◦ Pakistani CNIC scan option

◦ Driving Licence (DLS) scan option

• Image Capture & Upload Options:

◦ Live camera capture modal (Open Camera, Switch Camera, alignment frame guide, Capture Photo button)

◦ Image file upload / drag-and-drop (Upload Image)

◦ Automatic client-side image compression before saving

• OCR Extraction Capabilities (Unverified when Python FastAPI OCR server on port 8000 is stopped; falls back to mock data in Admin mode):

◦ CNIC Extracted Fields: Full Name, Father / Husband Name, CNIC Number, Gender, Country of Stay, Date of Birth, Date of Issue, Date of Expiry

◦ Driving Licence Extracted Fields: License Number, Full Name, Father / Husband Name, Date of Birth, License Category, Issue Date, Valid Upto, Licensing Authority

• Review & Edit Scanned Details Form:

◦ Editable fields for all extracted CNIC or Driving Licence attributes

◦ Identification Mark manual input field (CNIC)

◦ Rescan Document button

• Scanned ID Image Persistence:

◦ Automatic saving of scanned CNIC/Driving Licence image linked to the visitor profile

◦ Retry Saving ID Image button on registration confirmation screen if image storage fails

◦ Hidden from Operator registration screens after capture and visible only in Admin/Authorized Visitor Details views

## 7. Visitor Cards and QR Codes

• Visitor Card Number (`VC Card No.`) Management:

◦ Required VC Card No. input during normal visitor registration and Special Guest check-in

◦ Real-time active card conflict check (prevents assigning a card number currently in use by another checked-in visitor)

◦ Automatic release of VC Card No. for reuse once a visitor checks out

• Visitor Pass & Printable QR Badge (`VisitorBadgeModal`):

◦ GateShield branded header

◦ Visitor photo, full name, category badge, CNIC/ID number, host name, department, entry gate, check-in timestamp, visit number, and VC Card No.

◦ Unique pass QR code (GKP-...) for fast checkout scanning

◦ Print Visitor Pass button

◦ Close button

• Operator Login QR Card (`OperatorQrCardModal`):

◦ Printable GateShield Operator Access Card with unique operator number (OP-...), assigned gates, and encrypted login QR code (GKOP_...)

◦ Print Operator Card button

◦ Regenerate QR button (invalidates old QR code and issues a new one)

◦ Revoke QR Card button (disables QR login for that operator)

## 8. Check-In and Check-Out

• Operator 6-Step Visitor Check-In Wizard:

◦ Step 1 — Select Category: Visitor, Special Guest, Interview, Contractor, Delivery

◦ Step 2 — Visit Information: Host / Person to Meet input and Department dropdown (from configured active departments)

◦ Step 3 — Scan ID Card: Choose CNIC or Driving Licence and capture/upload image for OCR

◦ Step 4 — Review Scanned Details: Verify/edit extracted identity fields

◦ Step 5 — Visitor Photo: Live webcam capture (Capture Photo, Retake) or photo upload

◦ Step 6 — Registration Details: Phone Number (03XXXXXXXXX), VC Card No., Carrying Belongings? (Yes / No toggle + belongings description), and Complete Registration submit button

• Admin 3-Step Visitor Check-In Modal:

◦ Step 1: Category, Host Name, Department, and Document Type (CNIC / Driving Licence) scan & form review

◦ Step 2: Visitor photo capture/upload, phone number, VC Card No., and belongings

◦ Step 3: Registration confirmation, View Card, and Print Badge

• Check-Out Modal (`CheckOutModal`):

◦ Tab 1 — Scan QR Pass: Live camera QR scanner (QrScanner) that reads visitor pass QR code (GKP-...) and resolves active visit

◦ Tab 2 — Manual Search: Search active visitors inside by Name, CNIC, Phone, VC Card No., or Visit #

◦ Visit Verification & Exit Confirmation: Displays visitor photo, name, CNIC, host, department, entry gate, check-in time, duration inside, VC Card No., and carried belongings verification

◦ Already Checked-Out Detection: Displays warning banner with previous check-out timestamp and exit gate if pass was already checked out

◦ Confirm Check-Out button

## 9. Gate and Access Management

• Login Screens:

◦ Operator Login (`/login`):

▪ QR Card Scan Login tab (live camera scanner + Upload QR Card Image fallback)

▪ Credentials Login tab (Email Address, Password)

▪ Link to Employee Portal (/employee) and Admin Portal (/admin)

◦ Admin Login (`/admin`):

▪ Dedicated Administrator email & password sign-in

◦ Account Signup (`/signup`):

▪ Self-service account creation form (Full Name, Email, Password, Role)

• Manage Access & Operators Page (`/access` — Admin Only):

◦ Users & Operators table (User, Operator Number, Role, Assigned Gates, Status, Created Date, Actions)

◦ + Add Operator / Admin button (creates account, assigns gates, and automatically generates Operator QR Card for operators)

◦ Edit user button (update name, email, password, role, and assigned gate checkboxes)

◦ QR Card button (view, print, regenerate, or revoke operator login QR card)

◦ Activate / Deactivate user account toggle button

• Gate Authorization Rules:

◦ Administrators have access to all gates

◦ Operators only see and can check in visitors at their explicitly assigned active gate(s)

## 10. Reports and Records

• Reports & Analytics Page (`/reports` — Admin Only):

◦ Filter controls: From Date, To Date, Gate dropdown, Category dropdown, Status dropdown (All, Currently Inside, Checked Out), and Department text filter

◦ Summary metric cards: Total Entries, Currently Inside, Checked Out, and Unique Visitors

◦ Breakdown cards: Visits by Category and Visits by Gate

◦ Filtered visit records table

◦ Print Report button (formats page with GateShield • Security Audit Report print header)

◦ Export CSV button (downloads filtered report as .csv)

• Security Audit Logs Page (`/audit-logs` — Admin Only):

◦ Action filter dropdown (All Actions, CHECK_IN, CHECK_OUT, USER_LOGIN, USER_SIGNUP, CREATE_USER, UPDATE_USER, CREATE_GATE, UPDATE_PERSON_PROFILE)

◦ Paginated audit trail table (Timestamp, Action, Entity Type, Performed By, Details)

## 11. Notifications and Approvals

• Admin Employee Management Page (`/employees` — Admin Only):

◦ Tab 1 — `1. Employee Requests`:

▪ Status filter pills (ALL, PENDING, APPROVED, REJECTED)

▪ Search bar (by name, email, department, position, phone)

▪ Approve button (with confirmation modal)

▪ Reject button (with optional rejection reason modal)

◦ Tab 2 — `2. Employees`:

▪ Approved employees directory table

▪ Activate / Deactivate employee account button

◦ + Add Employee button (Admin directly creates an pre-approved employee account)

◦ Open Employee Portal shortcut link

◦ Refresh button

• In-App Notifications:

◦ Employee Portal Check-In / Check-Out Notifications: Real-time in-app notification sent to the inviting employee when their Special Guest is checked in at a gate (with gate name, operator, and VC card number) or checked out

◦ Operator Special Guest Arrival Toast & Badge: Live polling counter and audio/visual toast alert when an employee submits a new guest invitation

◦ Admin Pending Employee Badge: Live polling badge on the sidebar Employees menu item

• Email Notifications (`Partially Available` — requires `EMAIL_ENABLED=true` and valid SMTP credentials in environment; logs to `email_outbox` table and skips gracefully when disabled):

◦ Employee registration request confirmation email (to applicant)

◦ New employee registration request alert email (to Admin)

◦ Employee account approved email (to employee)

◦ Employee registration request rejected email (to employee, including admin note)

## 12. Settings and Other Features

• Department Management Page (`/departments` — Admin Only):

◦ Search bar (Search by department, HOD name, or WhatsApp number...)

◦ Total and Active departments counter

◦ Add Department button (Department Name, Head of Department (HOD), WhatsApp Number, Active toggle)

◦ Edit department button

◦ Activate / Deactivate department toggle button

◦ Delete department button (with confirmation modal; blocks deletion if linked to existing visits)

◦ Note: Department HOD WhatsApp number is stored and validated in Department Management, but automated WhatsApp message sending on check-in is not implemented.

• System Settings & Gates Page (`/settings` — Admin Only):

◦ Active Checkpoints & Gates Section:

▪ List of configured gates with gate name, description, and type (BOTH, ENTRY, EXIT)

▪ + Add Gate button and modal (Gate Name, Type, Description)

◦ System Configuration Parameters Section:

▪ Company / Facility Name input

▪ Badge ID Prefix input

▪ Overstay Threshold (Hours) input

▪ Save Settings button (Partially Available — settings are saved to the database, but badge prefix and auto-checkout/overstay hours are not enforced automatically during visit creation)

• Watchlist / Blacklist Page (`/blacklist`):

◦ Search bar (Search watchlist by name, CNIC, or reason...)

◦ Blacklisted individuals list with blacklist reason, CNIC, phone, and date added

◦ + Add to Watchlist button and modal (Full Name, CNIC Number, Phone Number, Reason for Blacklisting)

◦ Remove from Blacklist button

◦ View Profile link

• Localization, Branding & UI Features:

◦ Bilingual Operator UI (English LTR and اردو RTL layout support)

◦ Light Mode and Dark Mode theme switching with theme-aware GateShield logos

◦ GateShield animated loader (stationary hexagonal building mark with subtle inner gate-opening motion, access light, and perimeter scanning glow; respects prefers-reduced-motion)

◦ Interactive UI sound effects for operator step selection, navigation, check-in success, and guest arrival alerts